## GanttChart
YuhanTRUST그님티? Project Schedule | [7 empty] | Gantt Chart Template © 2006-2025 by Vertex42.com.
팀명: Hambugi
| Project Start Date | 2025-04-01 |  |  |  | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
[8 empty] | 2025-03-31 | [6 empty] | 2025-04-07 | [6 empty] | 2025-04-14 | [6 empty] | 2025-04-21 | [6 empty] | 2025-04-28 | [6 empty] | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19
 | time axis 2025-03-31 to 2025-05-25
WBS | TASK | LEAD | PREDECESSOR | START | END | % DONE | WORK DAYS | time axis 2025-03-31 to 2025-05-25
1 | 기획 |  |  |  | - |  | -
1.1 | 계획서 작성 | 박한별 |  | 2025-03-31 | 2025-04-02 | 100% | 3
1.2 | 개요서 작성 | 박한별 |  | 2025-04-03 | 2025-04-09 | 100% | 7
1.3 | 요구사항 분석 | 박한별 |  | 2025-04-04 | 2025-04-06 | 100% | 3
1.3.1 | 요구사항 정의서 작성 | 박한별 |  | 2025-04-06 | 2025-04-13 | 100% | 8
1.5 | 프로젝트 간트차트 제작 & 관리 | 박한별 |  | 2025-04-23 | 2025-05-03 | 80% | 11
1.6 | 메뉴 구조 정리 | 김은비 |  | 2025-04-30 | 2025-05-07 | 0% | 8
2 | 화면 설계
2.1 | 와이어프레임 설계 | 박한별 |  | 2025-04-09 | 2025-04-16 | 90% | 8
2.2 | 상세설계 | 김은비 |  | 2025-04-30 | 2025-05-21 | 0% | 22
2.3 | UI 디자인 | 김은비 |  | 2025-05-22 | 2025-06-09 | 0% | 19
3 | 자료 수집
3.1 | 프로그램 목록 수집 | 윤나래, 김려원 |  | 2025-04-09 | 2025-05-08 | 50% | 30
3.1.1 | 프로그램 목록 작성 | 윤나래, 김려원 |  | 2025-04-09 | 2025-05-08 | 50% | 30
3.2 | GoogleAPI 기능 테스트 | 김원정, 김은비 |  | 2025-04-09 | 2025-05-08 | 80% | 30
4 | 데이터 설계
4.1 | Google Sheets 구조 설계 | 김원정 |  | 2025-05-09 | 2025-05-21 | 0% | 13
5 | 구현
5.1 | 홈페이지(설명페이지) 개발 | 윤나래 |  | 2025-06-19 | 2025-07-05 | 0% | 17
5.2 | 로그인, 세션 구현 | 김은비 |  | 2025-07-06 | 2025-07-13 | 0% | 8
5.3 | 메인페이지 개발 | 박한별 |  | 2025-06-19 | 2025-07-05 | 0% | 17
5.3.1 | 티어계산 및 표시 기능 구현 | 박한별 |  | 2025-07-20 | 2025-08-02 | 0% | 14
5.4 | 튜토리얼 페이지 개발 | 윤나래 |  | 2025-07-06 | 2025-07-26 | 0% | 21
5.5 | 점수입력,수정 페이지 개발 | 김원정 |  | 2025-06-19 | 2025-07-19 | 0% | 31
5.6 | 이수 현황 페이지, 필터링 기능 구현 | 김려원 |  | 2025-07-20 | 2025-08-23 | 0% | 35
5.7 | 추천프로그램 페이지 개발 | 윤나래 |  | 2025-07-20 | 2025-08-23 | 0% | 35
5.8 | 탈퇴 기능 구현 | 김은비 |  | 2025-08-03 | 2025-08-23 | 0% | 21
6 | 테스트
6.1 | 기능 점검 및 오류 정리 | 김려원 |  | 2025-08-24 | 2025-09-06 | 0% | 14
6.2 | 버그 수정 | 김원정, 박한별, 윤나래 |  | 2025-09-07 | 2025-09-27 | 0% | 21
7 | 발표
7.1 | 중간 발표 | 김은비 |  | 2025-05-14 | 2025-05-14 | 0% | 1
7.1.1 | 중간 발표 자료 준비 | 김은비, 박한별 |  | 2025-05-03 | 2025-05-11 | 0% | 9
7.2 | 최종 발표 | 김원정 |  | 2025-11-05 | 2025-11-05 | 0% | 1
7.2.1 | 최종 발표 자료 준비 | 윤나래, 박한별 |  | 2025-10-01 | 2025-10-31 | 0% | 31
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.